## Sheet1
Cambridgeshire & Peterborough Local Growth Fund Projects as at 31 March 2019 |  |  |  |  | Financials | [7 empty] | Employment Outputs |  | Housing Outputs | Transport Outputs |  |  | Skills Outputs |  | Commerical Outputs | Business and Enterprise Outputs
| Project Theme(s) |  |  |  | Budget |  | Leverage |  |  | Financials to Date |  |  | Jobs Created to Date | Apprenticeships to Date | Housing Completed to Date | Roads to Date |  | Cycle Ways to Date | Learning / Training Floorspace to Date | Leaners Assisted to Date | Floorspace to Date | Businesses Supported to Date
Project Name | Project Theme | Project Status | Date Work Started | Date Work Completed | Total Budget | Of which LGF | Of which Public Sector | Of which Private Sector | Of which Third Sector | LGF Outturn | LGF Expenditure | Total non-LGF Expenditure | Jobs Created | Apprenticeships | Housing Units Completed | Km Length of Road Resurfaced | Km Length of Newly Built Road this period | Km Length New Cycle Ways | Area of new or improved learning/training floorspace (m2) | Number of New Learners Assisted (in courses leading to a full qualification) | Commerical floorspace created | Number of enterprises receiving grant support | Number of enterprises receiving financial support other than grants | Number of enterprises receiving non financial support
Name | Theme1 | Status | StartDate | EndDate | TotalBudget | LGFBudget | PublicLeverage | PrivateLeverage | ThirdLeverage | Outturn | LGFSpend | TotalNonSpend | EmpJobs | EmpApprentice | HousingComp | RoadResurface | RoadNew | RoadNewCycle | SkillsSpace | SkillsNewLearners | CommercialSpaceNew | BusinessSupportGrants | BusinessSupportNonGrant | BusinessSupportNonFinance
Whittlesey Access Phase 1 King's Dyke Crossing | Transport | Ongoing | 2016-07-01 | 2019-03-31 | 29981478 | 8000000 | 21981478 | 0 | 0 | 7224270.27 | 7224271.27 | 281000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ely Southern Bypass | Transport | Physical Completion | 2016-10-01 | 2018-06-01 | 36000000 | 6000000 | 30000000 | 0 | 0 | 22000000 | 22000000 | 12763831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bourges Boulevard Phase 1 | Transport | Completed Monitoring | 2014-01-04 | 31/07/2015 | 2100000 | 2100000 | 0 | 0 | 0 | 2100000 | 2100000 | 615000 | 240 | 0 | 200 | 4.964 | 0 | 2.45 | 0 | 0 | 32000 | 0 | 0 | 0
Bourges Boulevard Phase 2 | Transport | Physical Completion | 2016-03-01 | 2019-03-31 | 9200000 | 9200000 | 0 | 0 | 0 | 8870384.11 | 9199999 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A47/A15 Junction 20 | Transport | Completed Monitoring | 2016-03-01 | 2017-03-31 | 6300000 | 6300000 | 0 | 0 | 0 | 6300000 | 6300000 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wisbech Access Stategy | Transport | Ongoing | 2015-05-01 | 2021-03-31 | 1227434 | 1000000 | 227434 | 0 | 0 | 1000000 | 1000000 | 227434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TWI (The Welding Institute) Expansion | Innovation | Completed Monitoring | 2015-09-01 | 2018-03-31 | 3001063 | 2100000 | 0 | 901063 | 0 | 2100000 | 2100000 | 901063 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3390 | 0 | 0 | 0
Technical and Vocational Centre, Alconbury Weald | Skills | Physical Completion | 2015-05-01 | 2018-03-31 | 10500000 | 10500000 | 0 | 0 | 0 | 10155882.67 | 9646196 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2142 | 0 | 0 | 0 | 0 | 0
Agri-Tech Growth Initiative | Innovation | Ongoing | 2015-08-01 | 2021-03-31 | 4096000 | 3100000 | 996000 | 0 | 0 | 2736843.26 | 2942198.18 | 4366584.09 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0
Cambridge Biomedical Innovation Centre | Innovation | Completed Monitoring | 2015-12-01 | 2016-10-31 | 4064000 | 1000000 | 0 | 3064000 | 0 | 1000000 | 1000000 | 3064000 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2780 | 0 | 0 | 0
Haverhill Innovation Centre | Innovation | Ongoing | 2018-04-01 | 2020-03-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Peterborough Regional College Food Mfg Centre | Skills | Completed Monitoring | 2015-01-07 | 31/07/2016 | 1172000 | 586000 | 586000 | 0 | 0 | 586000 | 586000 | 586000 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0
Highways Academy | Skills | Completed Monitoring | 2015-03-01 | 2016-05-31 | 1490000 | 415000 | 75000 | 1000000 | 0 | 415000 | 415000 | 1075000 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 86 | 0 | 0 | 0 | 0
CITB Construction Academy | Skills | Total Completion | 2016-01-10 | 2017-12-29 | 946324 | 450000 | 0 |  | 496324 | 450000 | 450000 | 496324 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 511 | 0 | 0 | 0 | 0
EZ Plant Centre Alconbury | Skills | Total Completion | 2016-01-01 | 2016-03-31 | 154000 | 65000 | 0 | 40000 | 49000 | 65000 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Signpost 2 Grant | Business Support | Ongoing | 2016-02-01 | 2021-03-31 | 1500000 | 300000 |  | 1200000 |  | 204941.66 | 224708.3 | 19766.64 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Medtech Accelerator | Innovation | Ongoing |  | 2021-03-31 | 1200000 | 500000 |  | 700000 |  | 500000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lancaster Way Phase 1 Loan | Employment | Total Completion |  | 2021-03-31 | 1000000 | 1000000 |  |  |  | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lancaster Way Phase 2 Loan | Enabling Works | Total Completion |  | 2021-03-31 | 3680000 | 3680000 |  |  |  | 3680000 | 3680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lancaster Way Phase 2 Grant | Transport | Ongoing |  | 2021-03-31 | 5125000 | 1445000 |  |  |  | 581516 | 581516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manea and Whittelsea Stations | Transport | Ongoing |  | 2021-03-31 | 395000 | 395000 |  |  |  | 365345 | 365345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
M11 J8 | Transport | Ongoing | 2019-04-02 | 2021-03-31 | 5000000 | 1000000 | 4000000 |  |  | 0 | 0 | 0 | 0 | 0 | 6770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Terraview Loan | Enterprise | Ongoing | 2018-12-01 | 31/02/2021 | 554070 | 120000 |  | 434070 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0